## R1_Plan - Actual
Week ending | Preparation | CI | CD | Wrap-up
2021-07-11 | Setup the environments/toolset
2021-07-18 |  | Setup Azure Cloud Shell |  | Get video editing software
Configure GitHub Actions
2021-07-25 |  |  | Setup Azure Pipelines
Learn Locust
Implement Locust testing
2021-08-01 |  |  |  | Prepare demo video
2021-08-08 |  |  |  | Update the README
Submit the project
| Goals | Goals | Goals | Goals
| Working Azure, Github, etc. accounts | Working scaffolding in Azure that passes the tests | App deployed in Azure and passes the vertification tests | Project is ready to submit
Local development environment ready to work in

## R1_Plan - Original
Week ending | Preparation | CI | CD | Wrap-up
2021-07-04 | Setup the environments/toolset (4h) |  |  | Get video editing software (1h)
2021-07-11 |  | Setup Azure Cloud Shell (1h)
Configure GitHub Actions (4h)
2021-07-18 |  |  | Setup Azure Pipelines (4h) | Update the README (1h)
2021-07-25 |  |  |  | Prepare demo video (4h)
Submit the project (1h)
| Goals | Goals | Goals | Goals
| Working Azure, Github, etc. accounts | Working scaffolding in Azure that passes the tests | App deployed in Azure and passes the vertification tests | Project is ready to submit
Local development environment ready to work in

## Qtrly_Plan
Year 1
Quarter | Q1 | Q2 | Q3 | Q4
| Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun
Overall goal | Release 1 - MVP to meet assignment requirements | Transition to one platform for CI/CD | Improve JSON API with additional methods | Website for predictions via GUI
Sub goals | Research and learn CI/CD with GitHub + Azure | Research cloud platform for CI/CD & prepare transition plan | TBD | TBD
| Implement CI/CD as per assignment requirements | Transition to selected platform
Prepare project documentation
|  | Update docs | Update docs | Update docs